## Sheet1
Final Completion Checklist
Project Name: | [6 empty] | Project Number:
Location:
*/NR |  | when received
1 |  |  | Architect | Certificate of Substantial Completion AIA doc prepared by Architect |  |  |  | Date of:
2 |  |  | Architect | Architects Certificate of Punch List Completion (Letter from Design Professional).
3 |  |  | Contractor | Fire Alarm System Test Report and sign-off by system manufacturers Rep.
4 |  |  | Contractor | Sprinkler Test Reports/sign-off by qualified/certified installer.
5 |  |  | Contractor | Certificate of Occupancy from local Municipality. |  |  |  | Date of:
6 | ** |  | Contractor | Electrical Permit sign-off by State or Local Electrical Inspector.
7 | ** |  | Contractor | Plumbing Permit sign-off by State or Local Plumbing Inspector.
8 |  |  | Contractor | Elevator Certificate of Inspection (if applicable)
9 |  |  | Contractor | Consent of Surety to release final payment.
10 |  |  | Contractor | Requisition for all items excluding items listed on Incomplete Work Escrow list… (item #16)
11 |  |  | Contractor | Lien Releases (MaineHousing's Contractors Final Certificate and Release Form)
12 |  |  | Contractor | O&M Manuals (deliver to Owner)... Owner to confirm receipt
13 |  |  | Contractor | Warranty information to Owner (e.g. Roofing, Boilers, Windows, etc.)... Owner to confirm receipt.
14 |  |  | Contractor | As-Built Drawings (Contractor to deliver to Owner)… Owner to confirm receipt
15 |  |  | Contractor | Evidence of satisfactory Lead Based Paint clearance testing (if applicable)
16 |  |  | All | Incomplete Work Escrow in the amount of:
17 |  |  | Owner | As-built Alta Survey w/certification (may be waived if construction did not increase footprint)
18 |  |  | Owner | Blower Door Test Report
19 |  |  | Owner | NPS Part 3 Approval (required for Historic Tax Credit projects only)
20 |  |  | MH | Accessibility Standard/ Field Verification report by MaineHousing Construction Analyst
21
| * | required |  | NR not required | ** | Required unless covered by Municipalities Certificate of Occupancy
Construction Services has received and reviewed the documents above and find them suitable to satisfy project
closeout/completion per Construction Services requirements.
name here/ Construction Analyst | [7 empty] | Date:
Donald R. McGilvery/ Construction Sevices Manager | [7 empty] | Date:
FOR MAINEHOUSING USE ONLY. NO RELIANCE OF ANY KIND BY OTHERS.